## Jack
Date | Time (Hrs) | Worked on:
2025-09-21 | 1 | Organizing code and getting environment set up, forked repo to share with other group members
2025-09-28 | 3 | Started AI Auto solver, worked on cleaning up some code
2025-09-30 | 4 | Finished AI auto solver, added AI selection color, added compatibility for all difficulties with the AI and solver menus
2025-10-01 | 2 | Debugging/review of added code
2025-10-04 | 0.5 | Finished the person-hours text file to get ready for submission
TOTAL HOURS | 10.5

## Zhang
Date | Time (Hrs) | Worked on:
2025-09-21 | 2 | setting up go and it not working
2025-09-22 | 7 | Created a makefile that will actually compile the program. Spend a lot of time researching for missing dependencies and getting window exe to work(it did not). Added menu for AI and Single-Player mode
2025-09-23 | 2 | looking at the code and trying to understand the logic
2025-09-24 | 9 | research Go langauge handling of state. Implemented easyAI, set up future logic for HardAI and MediumAI, implemented the turn-based logic for AI mode
2025-09-29 | 0.5 | Try to implemented time.sleep for AI, but unsuccessful
2025-10-03 | 1 | fix bugs
TOTAL HOURS | 19.5

## Evan
Date | Time (Hrs) | Worked on:
2025-09-29 | 1 | Set up mediumAI.go file by utilizing the AI function of easyAI.go, cleaned up code
2025-10-01 | 2 | Set up mediumAI.go implementation 1 (using stack), and cleaned up code
2025-10-02 | 7 | Completed implementation 1, encountered index_out_of_bounds error, bug fixing, cleaned up code
2025-10-03 | 5 | Fixed index_out_of_bounds error, finished implementation 2 (number tile), and cleaned up remaining code to finish mediumAI.go
TOTAL HOURS | 15

## Alex
Date | Time (Hrs) | Worked on:
2025-09-23 | 2 | TItle screen / menu touchups
2025-09-23 | 2.5 | Restart Button & title button on win/loss
2025-10-03 | 2 | digram for the program architecture
Total | 6.5 hours

## Ian
Date | Time (Hrs) | Worked on:
2025-10-03 | 5 | Hard A.I and QA Testing
TOTAL HOURS | 5